## Slide 1
Guangzhou, December 13th, 2016
GSAFC
Sales Force Effectiveness (SFE) Project (Step 1: Solution Design)
3rd Steering Committee Meeting
Prepared by Project Management and Core Project Team
Prepared for Steering Committee
GSAFC Participants:
Gilbert RANOUX, Su HU, Yidong LUO, Alban DELAMARZELLE, Haicheng SU, Jinming ZHOU, Ming WEN, Yuhong LIU, Li ZHOU
BearingPoint Participants:
Yvon Donval, Vanny FEI, Guolu ZHAO, Sunny WANG, Peter PAN
FINAL VERSION, including results

## Slide 2: Today’s Steering Committee Meeting is scheduled to review the project status, acknow-ledge Phase 2 & 3 progress & results, agree on next steps and close-out SFE project step 1
Executive Summary – Project Results
Project Team successfully completed:
Preparation and execution of Sales Force Engagement Workshops in Zhengzhou (G7, Oct. 18th), Ningbo (G2, Oct. 20th), Suzhou (G5, Oct. 25th), and Taiyuan (G6, Oct. 27th) regarding key topics: 1. sales force performance factors, 2. sales process map, 3. sales training model, and 4. sales communication & reporting, incl. KPIs
Preparation and execution of 15 in-depth benchmark interviews with SAIC-GMAC regarding key topics: 1. sales team organization, 2. training team organization, 3. sales budget management mechanism, and 4. eCommerce business
Preparation and execution of multiple individual alignment meetings and group discussions regarding
  the sales team organization (incl. separation of strategy, governance and operational tasks)
  the adjusted sales management model
  the sales process map and process documentation methodology
  the sales training model, and
  the sales compensation model (aligned with HR)
Creation of the final report, incl. change initiatives and implementation roadmap (for SFE Project Steps 2 and 3)
Preparation and execution of 3rd Steering Committee Meeting, incl. decision proposals to
  confirm phase 2 and 3 results, incl.
  agree on close-out activities of SFE Project, Step 1, and
  agree on next steps to make the change

## Slide 3
  Overview of Project Status
  Phase 2 (Design Solution): Summary of key final report results
  Phase 3 (Fine-Tuning): Review of implementation roadmap
  Decision Proposals and Next Steps

## Slide 4
In Phase 2 & 3 the project team worked on the solution design and its alignment across the various stakeholders and created an implementation roadmap
Approach of Phase 2 & 3
The final report reflects the result of
  the GSAFC Sales Strategy design (Chapter B), and
  the detailed TO BE solution for Sales Operations (Chapter C) based on eight design for performance topics
In addition, the final report also includes Change Initiatives for each design for performance topic, which are translated into a milestone plan and implementation roadmap (Chapter D)
Additional information (e.g. work documents) is stored in the appendix (Chapter E)

## Slide 5: Core team addressed activities as agreed – TO BE Solution for eight performance topics, incl. roadmap are completed, communication package and sounding board are pending
Project Approach – Adjusted Milestones and Time Schedule
  Phase 1: “Diagnosis”
  Project Set-up
  Current State Analysis (= internal diagnosis)
  Benchmarking Survey (= external diagnosis)
  Diagnosis Report Creation & Discussion
  Phase 2: “Design Solution” (Updated Scope & Plan)
  Updated Project Scope & Detailed Planning of Phase 2
  Prep. & Execution of Sales Strategy Workshops 1-3
  Prep. & Execution of Sales Process Workshops 1-3
  Prep. & Execution of Ext. Benchmarking (Deep-Dive)
  (Bottom-up) Sales Team Engagement Workshops 1-4
  (Top Down) Sales Management Model WS 1-4
  Training Model/ HR & Other Topics
  Phase 3: “Fine-Tuning”
  Updated Solution Concept
  Roadmap, incl. Milestones
  Prepare Communication Package
  Decision Proposal
  Steering Committee Meeting
  Sounding Board Meeting
  Weekly Core Team Meeting
2016
week 1-4
week 5-8
week 9-12
week 13-16
week 17-20
week 21-24
week 25-28
Project Milestones and Time Schedule in Weeks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
May/June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | Dec. | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Phase 1 Diagnosis
Phase 2: Design Solution
1
Ph 3: Fine- Tuning
11
12
13
14
Onboarding 30.05.2016
09.08. Diagnosis Report
02.08. Benchmarking Results
02.08. Internal Analysis Results
Updated Sales Mgt. Model
Training Materials
Roadmap
Decision Proposal
Steering Committee
Sounding Board
Weekly Core Team Meeting
Project Milestone
06.06.16
04.07.16
16.08.16
13.10.16
13.12.16
TBD
We are here
✔
✔
✔
✔
11.08.16
30.09.16
Sales Strategy
Sales Process Map
3
2
4
✔
✔
✔
6
✔
5
7
8
9
10
Add. Ext. BM results
Input for Sales Mgt. Model
Sales Mgt. Model
Other Results
✔
✔
✔
(✔)
(✔)
(✔)
(✔)
(✔)
(✔)

## Slide 6
Project Status Report
We are confident that the SFE Project, Step 1 can be finished until Dec 16th as scheduled, if today’s Steering Committee confirms the results and decision proposals as presented
Scope
  Phase 2 scope was covered as agreed in 2nd Steering Committee
  Key deliverable is the final report which includes
    Results of the Sales Strategy design
    Detailed solution proposals regarding eight design for performance topics, incl. benefits and impact on organization, processes and technology
    High-level implementation roadmap, change initiatives incl. key milestones
Status
  N.a.
Mitigation Measure
Time
  Open tasks are (if today’s Steering Committee approves the presented results)
    Complete final report version, incl. implementation roadmap and appendix
    Complete communication package and prepare last Sounding Board Meeting
    Complete project documentation of SFE project, step 1 and hand-over
Status
  N.a.
Mitigation Measure
Budget
  Last external invoice (December) to be issued after completion of hand-over activities
Status
  N.a.
Mitigation Measure

## Slide 7
  Overview of Project Status
  Phase 2 (Design Solution): Summary of key final report results
  Phase 3 (Fine-Tuning): Review of implementation roadmap
  Decision Proposals and Next Steps

## Slide 8
GSAFC Sales Strategy is defined along six elements, which reflect the core of the strategy & its operationalization – we recommend an annual review of the implementation status
Sales Strategy Definition – Core Elements
1. Winning Aspiration
2. Where
to Play
3. How to Win
4. Design for Performance
5. Change Initiatives
6. Make the Change
Strategic Level
Operational Level
Transfer to GSAFC operations

## Slide 9
Goal of the GSAFC Sales strategy is to reduce operational complexity, improve the alignment, and systematically strengthen the sales team at strategic and operational level
Sales Strategy Definition – Purpose of GSAFC’s Sales Strategy
GSAFC Sales Team –Today
GSAFC Sales Team – Tomorrow
From: Marketing-driven, task-oriented
To: Sales process-driven, empowered by analytics
Marketing-driven
Sales analytics
Sales trainings
Sales support
Sales Operations
Low governance
Informal Communication
Hero-driven culture
Overlapping roles
Easy-to-achieve bonus
Lack of career options
NSM
RMs
DMs
CMs
FAs
FCs
FCs
Top-Down Push
targets
products
methods
Marketing
(Digital) Products
Promotions
eCommerce
products
targets
methods
Sales Operations
Aligned communication
Transparent targets
Available reports
Clear responsibilities
Fair performance KPIs
Performance-oriented career & bonus model
Sales Governance
Strong sales analytics
Standardized trainings
Standardized processes
Aligned
campaigns
DMs
NSM
RMs
…
Aligned

## Slide 10: Eight operational topics were addressed by the project team with a clear structure that describe the detailed solution design – focus is on improving the sales force effectiveness
Sales Strategy Definition – 8 “Design for Performance” topics improve GSAFC‘s Sales Operations
1. Sales Organization
2. Sales Governance
3. Sales Process Map (incl. 3 specific process examples)
4. Sales Channel Management
5. Sales Communication & Reporting
6. Sales Performance Measurement
7. Sales Training Model
8. Sales Compensation Model
1. Facts & Figures (AS-IS)
2. Guiding Principles (TO-BE)
3. Guidelines (AS-IS vs. TO-BE)
5. Change Initiatives (TO-BE)
Structure per Topic
4. Benefits/ impact (of TO-BE)

## Slide 11: Top 11 guiding principles serve as overall strategic guideline for GSAFC stakeholders to ensure alignment regarding the strategic direction of the GSFAC sales team development
Sales Strategy Definition – Top 11 Guiding Principles
Clear separation between Sales and Marketing tasks allows a transparent split of roles & responsibilities between both departments which increases the empowerment of both teams and allows a stronger focus on internal efficiencies and external effectiveness
Sales function is empowered by ensuring that important sales-related tasks and roles & responsibilities are defined within the sales function
Sales & Marketing Division has a transparent, goal-oriented, standardized annual sales budget and sales target planning process
The National Sales Manager (NSM) is the process sponsor of the sales process map and responsible for the overall performance efficiency and effectiveness of the sales processes
The GSAFC Sales Process Map is defined and characterized by Sales Management, Sales Execution and Sales Support processes
Regional Manager (RM)/ National Sales Manager (NSM) headcount is calculated by the task require-ments and governance ratio guideline on each hierarchy level
Dealer (DLR) coverage at District Manager (DM) level (= no. of dealer shops) is the baseline for head-count calculation; it is calculated by the task & time requirements specified for the position (e.g. DLR visit frequency)
Sales team internal communication is established in a transparent manner and established across all sales hierarchy levels on a regular basis – it covers both, top-down and bottom-up, communication channels
KPIs must be measured regularly and are sales-oriented in a way that they promote the sales orientation of the sales team - KPI reports are accessible for the affected employees
Sales training courses and curriculum are designed by the sales training team and regularly updated
Sales Team’s total compensation is competitive compared with the industry average standard
In total, approx. 70 guiding principles were identified and discussed during the SFE project
They served as input for the TO BE solution design discussions and to create an overall alignment regarding the strategic direction

## Slide 12
Design for Performance topics reflect the sales management model and how it can be operationalized based on Guiding Principles, TO BE Solutions and Change Initiatives
Design for Performance Topics
Design for Performance
3. Sales Process Map
4. Sales Channel Management
7. Sales Training Model
6. Sales Performance Measurement
1. Sales Organization
2. Sales Governance
For this purpose
Guiding Principles,
TO BE Solutions and
Change Initiatives
were specified
Transfer to operational
level
(Part C)
8. Sales Compensation Model
5. Sales Communication & Reporting

## Slide 13
1. Sales Organization – TO BE Solution (Sales & Marketing function – Optimization plan)
DECISION PROPOSAL 1 Future sales organization shall cover a broader functional scope which is reflected by a central Sales Operation & Planning function, and the regional Channel Sales function
As Is – Sales & Marketing Function
To Be – Sales & Marketing Function
Sales
(1 National Sales Manager, 2 Assistant, 1 Wholesales Coordinator)
Marketing & Sales Support
Sales & Marketing Function
4+237
G 1
55
G 2
31
GS 4
33
GS 5
28
GS 6
43
GS 7
44
1+22
PR
1
Marketing
5
Business
Development
10
Sales Support
5
KAM
3
Sales & Marketing Function
Channel Sales
Sales O&P
Marketing
Sales Execution Staff Only
Set up By Per Sales Channel
Channel Mgr.
Regional Mgr.
District Mgr.
…
KAM
Sales Training
Sales Operation & Optimization
Sales Planning & Analytics
New Channels
(e.g. White Brand, used car)
PR
Marketing
Product Development
E-Commerce
Decision Proposal 1

## Slide 14
2. Sales Governance – TO BE Solution (Sales target set-up mechanism)
DECISION PROPOSAL 2 Future Sales Target Management will have a clear linkage with budget set-up, and will also be supported with a quarterly review and update mechanism to guide daily budget usage
1. Sales Target Set Up
Top Down
Process
Bottom Up
Process
Mgt. Review
Process
2. Sales Budget Set Up
S&M Total Budget
HQ / Channel Allocation
Regional / District Allocation
3. Sales Forecast & Adjustment
Sales Monthly Review
Mgt. Quarterly Review
Target Review / Adjust
Budget Review / Adjust
4. Sales Budget Management
Budget Apply
Budget Approve
Execution Monitor
Spend / Performance Analysis
Yearly Process
Monthly Process
Monthly Process
Yearly Process
Other Sales Management Mechanism
Sales KPI Management
Sales Compensation Management
Sales Communication & Reporting
Monthly Review
Quarterly Adjust
Target & Budget Linkage
Performance Monitoring
Performance Monitoring

## Slide 15
2. Sales Governance – TO BE Solution (Mgt. Decision on S&M Division Budget Set-Up Mechanism)
DECISION PROPOSAL 3 GSAFC’s management team should provide S&M departments with clear guidance on total budget scope, and detailed instruction on sales activity allowance per RTL contract
Management Decision #1
What is the right rationale for GSAFC’s S&M Division Budget?
X% over annual RTL value
Management Decision #2
How much sales activity budget should be given to sales force per single RTL contract?
X CNY per Contract*
*depends on overall sales situation, competition situation, risk policy and OEM network)
Sales Budget Management Mechanism to be set up by Sales Organization
4. Sales Budget Management
Budget Apply
Budget Approve
Execution Monitor
Spend / Performance Analysis
Sales Budget Management Process has been established (Please refer to corresponding process chapter)
Note: Management Decision #1 and #2 shall to be taken until January 30th, 2017

## Slide 16
1+2. Sales Organization & Governance – Benefits & Change Initiatives
DECISION PROPOSAL 4
Tangible and intangible benefits are connected to the proposed sales organizational & governance changes – to realize them, we recommend to consider eight change initiatives
Benefits of sales organizational & governance changes | Sales Organization Create a shared vision of both departments (= sales & marketing) Reduce collaboration issues Empower the sales team to manage their operational sales activities more efficiently Improve sales training concepts, plans and content to increase the training quality Governance Ensure transparency regarding the sales budget is defined and allocated Empower the sales force to better response to market and dealer requirements Develop ownership culture and trust to the sales force to allow them allocate the resource to drive sales
Change Initiatives | Agree on sales strategy and organizational changes within the S&M Division (until Jan 30th 2017) Review, agree and prepare sales target set-up & budget allocation processes (until Jan 30th, 2017) Communicate & assign new sales operation & planning department and roles (on Feb 15th, 2017) Migrate tasks & roles from Marketing to Sales departments (until Mar 31st, 2017) Execute sales target set up & budget allocation process for 2017 (until Mar 31st, 2017) Specify sales operation & planning department & section-specific concepts (until Jun 30th, 2017) Roll-out new sales O&P organization, incl. roles & responsibilities (on Jul 1st, 2017) Execute sales target set up & budget allocation process for 2018 (until Nov 30th, 2017)

## Slide 17
In context with Sales Organization and Governance, we kindly ask the Steering Committee to approve the following four decision proposals
Decision Proposals 1-4
Decision Proposal 1:
  The Steering Committee approves the proposed organizational changes to empower the Sales Organization by adding a Sales Operation & Planning Department, incl. a
      Sales Training Section
      Sales Operation & Optimization Section
      Sales Planning & Analytics Section
      New Channel Management Section

Decision Proposal 2:
  The Steering Committee approves the concept of a sales target and sales budget mechanism, which needs to be clearly linked to a quarterly review and update mechanism to guide sales budget usage

Decision Proposal 3:
  The Steering Committee agrees that the Top Management team needs to establish a transparent rationale behind the calculation of the S&M Division budget (e.g. % of total retail contract volume) and the sales activity budget (e.g. CNY allowance/RTL contract*) – an initial decision will be made by the Top Management, e.g. until Jan 30th, 2017.

Decision Proposal 4:
  The Steering Committee agrees to the identified benefits and change initiatives

*depends on overall sales situation, competition situation, risk policy and OEM network)

## Slide 18
Design for Performance Topics
Design for Performance
3. Sales Process Map
4. Sales Channel Management
7. Sales Training Model
6. Sales Performance Measurement
1. Sales Organization
2. Sales Governance
For this purpose
Guiding Principles,
TO BE Solutions and
Change Initiatives
were specified
Transfer to operational
level
(Part C)
8. Sales Compensation Model
5. Sales Communication & Reporting
Design for Performance topics reflect the sales management model and how it can be operationalized based on Guiding Principles, TO BE Solutions and Change Initiatives

## Slide 19
3. Sales Process Map – TO BE Solution (GSAFC Sales Process Map)
DECISION PROPOSAL 5
The project team mapped the GSAFC Sales Process Map with GSAFC’s Corporate Process Map – final alignment between sales team and Q&I section is still pending
Management
Processes (MP)
Core processes (CP)
Support
Processes (SP)
MP.04 Change management
MP.05 Project management
CP. 10
Retail business
CP. 20
Wholesale business
CP. 30
Business partner relationship management
SP.01 HR management
SP. 04 Legal & Compliance
SP.02 Admin
SP.05
Treasury
SP.06 Accounting & Tax
MP.03 Cost & Planning management
Sales Strategy
Create sales strategy
Delivery and communication
Monitor and update of sales strategy
Sales organization and resource planning
Sales Target & Budget
Set up total sales annual target
Create total sales annual budget
Sales target review and adjustment
MP.01 Company governance
Sales Communication & Reporting
Sales internal meeting
Sales external communication
Sales operational report mgt.
Sales support
Sales Performance & Incentive Mgt.
Review and set up KPIs
Review and set up incentive model
Sales performance report mgt.
PPIP (Improvement & coaching)
KPI review and bonus calculation
Training Management
Create Annual Training Plan
Training preparation
Training execution
Training assessment
Post-loan management for RTL
Credit freeze & Contract termination for RTL
Remarketing for RTL
Credit line
New dealer visitation preparation, WHL
Existing dealer visitation preparation, WHL
Proposal introduction to dealer, WHL
Collection of application materials
WHL approval & agreement
Floating mortgage registration
DAS system preparation, activation and training
Wholesale service
Dealer contract renew & update
Dealer receipt management
Credit freeze & Contract termination
Remarketing to dealer
MP.02 Risk management
RTL Risk management
Pre-activation
Leads management of end consumer (Leads collection, leads analysis & direct mail)
Product intro. to end user
Customer loan application
Car mortgage of end consumer
Loan contract activation and disbursement
Business development
Sales Planning
New dealer development plan
Dealer visit plan
Dealer performance action plan
OEM relationship management plan
New dealer visitation preparation (including check mortgage registration), RTL
Existing dealer visitation preparation, RTL
Market Solution
Best practice model (Dealer AFC workshop)
Benchmark
Proposal introduction to retail management
Preparation for IT enablers for RTL
Customer service
RTL customer service
Remarketing to end consumer
Collection & Litigation
Collection and litigation for end consumer
Risk & Collection
WHL Risk management (stock audit, financial statements, violation)
SP.03 IT management
Points platform
POSM platform
Intranet
Expense platform
Query of BI database
Payment of service fee
Alignment pending

## Slide 20
DECISION PROPOSAL 6
GSAFC Sales Process map and documentation of TO BE sales processes will have a measur-able impact on the process performance and can be realized through six change initiatives
Benefits of the Sales Process Map Changes | Reduce task overlaps between the sales roles Support the collaboration between sales and other GSAFC departments (and sets a standard for other GSAFC Depts.) Increase process performance, which can be measured and continuously improved (based on critical to process <CTP>) Help new sales team members to better understand and get quickly familiarized with existing sales processes and their (new) tasks Strengthen the overall understanding and alignment regarding “how sales works at GSAFC” (= sales team spirit)
3. Sales Process Map – TO BE Solution Benefits & Change Initiatives
Change Initiatives | Prepare and execute training to sales leaders (by Q&I section), incl. BPM concept and process priority definition (until Jan 30th, 2017) Review, fine-tune & align on new sales process map & identify Tier 1 & 2 processes (until Jan 30th, 2017) Optimize Tier 1 TO BE sales processes, incl. formalized operational procedures (until Jun 30th, 2017) Support roll-out activities, incl. role & process trainings and coaching measures (until Sep 30th, 2017) Execute process performance measurement for Tier 1 processes (as of Jul 1st, 2017) Optimize Tier 2 TO BE sales processes, incl. formalized operational procedures (until Dec 31st, 2017)

## Slide 21
In context with the Sales Process Map, we kindly ask the Steering Committee to approve the following two decision proposals
Decision Proposals 5 & 6
Decision Proposal 5:
  The Steering Committee approves the concept draft of the Sales Process Map, the leveraged sales process documentation methodology and confirms the need to identify Tier 1 & 2 sales processes (until Jan 30th, 2017).

Decision Proposal 6:
  The Steering Committee agrees to the identified benefits and change initiatives


## Slide 22
Design for Performance Topics
Design for Performance
3. Sales Process Map
4. Sales Channel Management
7. Sales Training Model
6. Sales Performance Measurement
1. Sales Organization
2. Sales Governance
For this purpose
Guiding Principles,
TO BE Solutions and
Change Initiatives
were specified
Transfer to operational
level
(Part C)
8. Sales Compensation Model
5. Sales Communication & Reporting
Design for Performance topics reflect the sales management model and how it can be operationalized based on Guiding Principles, TO BE Solutions and Change Initiatives

## Slide 23
4. Sales Channel Management – TO BE Solution (Role & Responsibility Overview)
DECISION PROPOSAL 7
NSM/RM roles will be empowered – they jointly act as business planner, share the same vision regarding sales targets, and help to translate them into region-specific action plans
National
Sales Manager
(NSM)
District Manager (DM)
GAC Channel Sales Force
Strategy – channel strategy and collaboration
Planning – sales target and rolling forecast
Communication – management, cross department, and sales force meeting (especially regional specific action plan discussion)
  … is the owner of the sales channel
  … is the main executional role for sales target achievements
Dealer relationship management for RTL/WHS business
Single dealer level coaching (i.e. FA/FC)
Regional Manager (RM)
Regional OEM relationship management
DM coaching and design action plan (regional to district level)
Communication and reporting at regional level
  … is the interface to link market share with sales target at regional level
Sales Representative (SR)
  … is the candidate pool for DM, and utilized as the force to overcome exceeding dealer coverage
Help DM with administration and operational tasks (SR will be assigned to a DM as reporting line)
Gradually take over RTL/WHS sales operational tasks from low amount of DLR coverage to a full DM level dealer coverage
Financial Advisor
(FA)
  … is the special sales force of GSAFC staffed in strategic DLRs to act as a competitive differentiator
Responsible of RTL operation at instructed DLR shop
Promote GSAFC product to DLR and end customer
Perform value added tasks to GSAFC (including QC)

## Slide 24
Value Added
Non-Value Added
Regional OEM Relationship
20%
Transportation
20%
DM On-site Support
DLR Visit
40%
Regional Sales Planning
20%
4. Sales Channel Management – TO BE Solution (RM Capacity Allocation)
DECISION PROPOSAL 7
RM should focus on maintaining OEM relationship at regional level and provide one-on-one coaching to DM as well as fulfill monitoring and planning tasks at regional level
Management Instruction – RM Level
OEM relationship – each OEM channel to have two visits per half year
DM Management Ratio – On average each RM should manage 8 DMs in order to meeting DM on-site support frequency instruction
In the Past
In the Future
?
10 Regional OEM Conference Per Half Year
(quarterly communication with each of the 5 OEM channels)
DM Visit every 2 Months (with coaching report)
(4 visits per Month)
Key task of RM is to “train” the DM
Weekly Regional Meeting (report)
Monthly Sales Report

## Slide 25
4. Sales Channel Management – TO BE Solution (DM Capacity Allocation)
DECISION PROPOSAL 7
Increasing the focus of the DM on value adding sales execution activities is the most important goal of adjusting the core sales force role
Value Added
Non-Value Added
RTL Sales Negotiation
30%
Transportation
26%
Admin & Operation
26%
WHS Negotiation
9%
FA/FC Coaching
9%
Value Added
Non-Value Added
RTL Sales Negotiation
40%
Transportation
20%
Admin & Operation
5%
WHS Negotiation
15%
FA/FC Coaching
20%
Management Instruction – DM Level
Dealer Visit Frequency – On average once per month, key dealers twice per month
Dealer Coverage – On average 25 dealers per DM in order to meeting dealer visit frequency instruction
In the Past
In the Future
75%
Value Added
Activities

## Slide 26
4. Sales Channel Management – TO BE Solution (DM Value Creation)
DECISION PROPOSAL 8
Overall goal of the sales force activities must be to sustainably increase the percentage of business activation, active dealers and top dealers
DM Value Creation – Focus on sales execution and build dealer relationship
Dealer Activation – Focus on activating existing and new dealers
RTL/WHS Promotion – Promote GSAFC RTL/WHS products within activated dealers to achieve highest possible market share
Strategic Relationship Building – Through the relationship building within all hierarchy level of DLR to achieve strategic relationship
2016 – DLR Coverage
2019 – TO BE Ambitious
Total GAC Channel DLR – 2,000
Activated DLR – 1,700
Active DLR – 1,200
Amount of DLRs has regular and normal business
Total DLR
Activated DLR
Active
DLR
TOP DLR – 110
Amount of Top DLRs based on VIP policy (rolling every half year)
TOP
DLR
Activated Rate
86%
Active Rate
60%
TOP Rate
5%
1. DLR Activation
2. DLR Sales Negotiation
Total DLR
Activated DLR
Active
DLR
3. DLR Relationship Building
TOP
DLR
Activated Rate
95%
Active Rate
80%
TOP Rate
20%
DM Value Creation

## Slide 27
4. Sales Channel Management – TO BE Solution (DLR Coverage & DM headcount calculation)
DECISION PROPOSAL 9 Average DM dealer visit could be kept at 30, but the DM headcount and no. of dealers to be covered should be reviewed annually and gradually increased/ decreased*
DLR Segmentation
DLR Segmentation
DM Management Input
DLR Coverage per DM
Average DLR Coverage
Considering different segmentation of DLRs in one district, average DLR coverage per DM should be 25 DLRs per DM
DM Headcount
Based on 2016 estimation of total 2,000 DLRs, DM headcount: 80
Based on 2017 estimation of total 2,200 DLRs, DM/CM headcount: 88
DM Execution Monitoring
Ding Ding can support Sales Planning & Analytics Function to monitor DM daily visiting to DLRs
Requirement for Monthly Ding Ding DLR visit report amount should be 32
DLR Visit Frequency
AAA/AA – At Least Once every Two Weeks
DM Task Requirement
Efforts on Transportation
- should not exceed 20%
Visit DLR
- at least two DLRs per Day
DM Monthly Capacity
Consider the Requirements Above, DM should be able to conduct
- on average 32 Visits per Month
Prerequisite – if DM can focus solely on sales objective achievement, but not any operation and aftersales activities
A – At Least Once every Four Weeks
DLR/DLR Group Segment | Definition
VIP DLR/DLR Group | TOP Performing in RTL
Key DLR/DLR Group | High Potential in RTL
Normal DLR/DLR Group | Activated
Non-Active DLR | Non-Activated
No DLR Group | Independent DLR
 | VIP DLR | Key DLR | Normal DLR | Non-Active DLR
VIP DLR Group | AAA | AAA | AAA | AAA
Key DLR Group | AAA | AAA | AA | AA
Normal DLR Group | AAA | AA | A | B
No DLR Group | AAA | AA | B | C
B/C – At Least Once every Two Months
* Key Assumption: The overall GAC dealer network will continue to grow

## Slide 28
4. Sales Channel Management – TO BE Solution (Role & Responsibility Overview)
DECISION PROPOSAL 9
Proposed headcount at RM/DM level is calculated based on task allocation and role require-ments in order to achieve the desired service level
District Manager (DM)
Regional Manager (RM)
2016*
2019
DLR: 2,000
DLR: 2,500
  Headcount: 7 RMs
  DM Mgt. Ratio: 1:9
  Headcount: 12 RMs
  DM Mgt. Ratio: 1:8
  Headcount: 62 DMs
  DLR Coverage: 32
  Avg. DM productivity**
  3,500 RTL contract / Year
  Headcount: 100 DMs
  DLR Coverage: 25
  Avg. DM productivity
  4,400 RTL contract / Year
* Calculation is based on 2016 actual data ** Average DM productivity is calculated by total retail contract divided by DM headcount

## Slide 29
4. Sales Channel Management – TO BE Solution (GAC Channel Sales development plan)
DECISION PROPOSAL 9
In total, we expect that the sales force team will decrease to approx. 164 staff by 2019 – while CM will be replaced by SR, FA role will be reduced to a stable level (of approx. 30 staff)
DLR Amount Forecast based on OEM information
National Sales Mgr.
Regional Mgr.
District Mgr.
City Mgr.
Financial Advisor
GAC Channel
Sales Organization
2016
2017
2018
2019
DLR: 2,000
DLR: 2,200
DLR: 2,400
DLR: 2,500
Sales Rep.
1
10
80
19
135
0
1
11
88
15
80
0
2
12
96
10
50
5
2
12
100
0
30
20
Keep Steady Headcount Increase at NSM/RM/DM Level
1 : 10
1 : 8
TTL: 91
TTL: 124
245
TOTAL SALES FORCE TEAM
195
175
164
1 : 8
1 : 6
Keep Steady Headcount Decrease at CM/FA Level & Replace CM with SR
TTL: 154
TTL: 50
Remark: 2016 RM/DM headcount is the estimation based on modeling result, not actual data

## Slide 30
4. Sales Channel Management – Benefits & Change Initiatives
DECISION PROPOSAL 10
To realize the benefits of a more effective Sales Channel Management and a clear roles & responsibility structure, we recommend to implement seven change initiative
Benefits of the Sales Channel Management Changes | Adjusted channel management and sales roles help to reduce overlaps, redundant activities, and increase the focus on sales will increase the motivation of the sales team promotes the collaboration across the sales levels allow GSAFC to better serve the GAC dealer network in a growing market form the basis for establishing a standardized sales management practice that is scalable emphasize the importance of mentoring, managing the team support to creating a GSAFC sales spirit
Change Initiatives | Agree on adjusted channel sales management structure and roles & responsibilities (until Jan 30th, 2017) Communicate corner stones of the new sales channel management (on Feb 15th, 2017) Specify headcount, dealer segmentation & coverage calculation methodology (until Mar 31st, 2017) Prepare adjustment of GSAFC Sales Channels, incl. region and district structure (until Jun 30th, 2017) Prepare training & coaching approach and documents (until Jun 30th, 2017) Announce and roll-out new GSAFC sales channel structure (on Jul 1st, 2017) Roll-out new Channel Sales organization, incl. role & process trainings and coaching (as of Jul 1st, 2017)

## Slide 31
In context with Sales Channel Management, we kindly ask the Steering Committee to approve the following four decision proposals
Decision Proposals 7-10
Decision Proposal 7:
  The Steering Committee approves the updated concept of sales roles & responsibilities, namely Regional Manager (RM), District Manager (DM), and Sales Representative (SR), incl. a limited no. of Financial Advisors (FA task force)

Decision Proposal 8:
  The Steering Committee agrees that the overall goal of the sales force activities must be to sustainably increase the percentage of dealer business activation (e.g. to 95%), the number of active dealers (e.g. to 80%) and the percentage of top dealers (e.g. to 20%) (Note: adjustments prior to launch are possible)

Decision Proposal 9:
  The Steering Committee agrees that – to achieve these sales targets –
    the headcount ratio of RM/DM must be reduced (e.g. from 9 to 8),
    the DLR coverage ratio per DM must be reduced (e.g. from 32 to 25), and
    the sales force team will decrease to approx. 164 staff by 2019 – while DM will be increased, CM will be replaced by SR, and FA role will be reduced to a stable level (of approx. 30 staff)
    As a result, the average number of DLR contracts per DM will be increased (e.g. from 3500 to 4400)
    Innovative DLR segmentation, network coverage calculation and management methods (supported by digital toolbox) need to be specified, agreed and rolled-out

Decision Proposal 10:
  The Steering Committee agrees to the identified benefits and change initiatives


## Slide 32
Design for Performance Topics
Design for Performance
3. Sales Process Map
4. Sales Channel Management
7. Sales Training Model
6. Sales Performance Measurement
1. Sales Organization
2. Sales Governance
For this purpose
Guiding Principles,
TO BE Solutions and
Change Initiatives
were specified
Transfer to operational
level
(Part C)
8. Sales Compensation Model
5. Sales Communication & Reporting
Design for Performance topics reflect the sales management model and how it can be operationalized based on Guiding Principles, TO BE Solutions and Change Initiatives

## Slide 33: DECISION PROPOSAL 11 To cover communication across sales internal hierarchies and with external departments, 5 additional communications are proposed to be considered for implementation
RM weekly meeting (Sales leader weekly meeting)
National-wide sales call meeting (National Sales & Marketing monthly meeting)
National sales convention (National Sales & Marketing semiannual meeting)
Monthly department manager meeting
Price committee meeting (Monthly review with Finance)
NPL meeting (Monthly review with Credit Risk Dept.)
CCC meeting (Weekly meeting with WHS Acceptance Dept.)
5. Sales Communication & Reporting – TO BE Solution (New Sales Communication Structure)
7 Existing Communications
Sales Internal
Sales & Marketing Internal
With Top Management
With HQ Departments
Weekly Regional Sales Meeting
Annual National Sales Survey (new)
Weekly Sales & Marketing Leader Meeting
Monthly sales review with top management
Bi-monthly Review with relevant HQ departments e.g. IT, Operations, Credit Risk
5 New Communications

## Slide 34: DECISION PROPOSAL 11 Establish Monthly sales review with top management for detailed information sharing on sales operational progress and issues
5. Sales Communication & Reporting – TO BE Solution (4. Monthly Sales Review with TM)
Share operational details of sales activities with top management
Discuss on key sales issues
Objectives
1 hour
Duration
Contents
Monthly/Face-to-face meeting
Frequency
GM
EDGM
Head of Sales & Marketing division
National Sales Manager
Head of Sales O & P dept.(Owner)
Participants
Monthly sales review with top management meeting minutes, including:
Key decisions
Sales team to-do list for next month
Output
With Top Management
Proposal
Agenda | Duration | Executed by
Sales performance overview by OEM, region, district, and dealer | 10 min | National sales manager
Sales update on promotions and products | 10 min | National sales manager
Progress update on sales relevant projects | 10 min | Head of Sales & Marketing division
Discussion on key sales issues and solutions | 30min | All

## Slide 35
以上内容仅为本文档的试下载部分，为可阅读页数的一半内容。如要下载或阅读全文，请访问：https://d.book118.com/737050066113006030